## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
2225-swen-261-06-f-cardsharks | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. |  |  | Pass | YK NS
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. |  |  | Pass | YK NS
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. |  |  | Fail | YK NS; no message pops up
| Given that I am on the products page when there are products in the inventory then I see each product and short description. |  |  | Fail | YK NS; not on product page
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. |  |  | Fail | YK NS; not on product page, have to click item to click add to cart button
As an Admin I want to be able to edit the inventory with UI to make edits to the database. | Given an admin is signed in when they view the homepage then they should have a button to open a page to edit inventory. | Pass |  | Pass | YK NS
| Given an admin is on the inventory page, when they click on a product, then they are brought to a page where they can edit the details of the product | Pass |  | Pass | YK NS
| Given an admin is on the website when they open the inventory ui then it displays the cards from the db to edit. | Pass |  | Pass | YK NS
| Given an admin is on the website when they open the inventory ui then there should be a button to add a card. | Pass |  | Pass | YK NS
| Given an admin is on the website when they open the inventory ui then there should be a button to remove a card. | Pass |  | Pass | YK NS
As a Customer I want to see a means to add/delete/edit my payment information so that I can use it next time. | Given I am logged in and on the account page, when I click on the edit payments button, I am taken to a page where I can edit my payments. |  |  | Pass | YK NS
| Given I am on the payment page and have payment information typed in to the text field, when I click add payment, the payment is added to my account. |  |  | Pass | YK NS
| Given I have Payment information stored, when I press the X button next to it, then it is removed from my account |  |  | Pass | YK NS
| Given I have payment information stored, when I navigate to the payment page, my stored payments are displayed. |  |  | Pass | YK NS
As a user I want to create or delete an account so that I can use the store. | Given I go to accounts tab when create an account with given user then I create an account if there's no existing account. |  |  | Pass | YK NS
| Given I go to accounts tab when I delete an account logged in as a user then I delete an account. |  |  | Pass | YK NS
As a user I want to create or delete an account so that I can use the store. | Given I'm not logged in when I click the login button then if the account exists I log in. | Pass |  | Pass | YK NS
| Given the username is admin when I log in then I am logged in as an admin. | Pass |  | Pass | YK NS
| Given I am logged in, when I leave the page or press logout, I'm am no longer logged in. | Pass |  | Pass | YK NS
| Given I input any user name with an existing account other than "admin", when I log in, then I am logged in as a customer | Pass |  | Pass | YK NS
As a customer I want to be able to search for a specific item so I can purchase it. | Given I search for a product, when products exist that match the search term, then they are displayed. | Pass |  | Pass | YK NS
| Given I search for a product, when there is no product that matches the search criteria then an "item not found" message will show | Pass |  | Pass | YK NS
As a customer I want to be able to add items to my cart so I can save them for later purchase | Given I'm looking for a product page, when I click add to cart the product is added to my cart | Fail | JM, 3/27, Test failed because solution was not properly implemented | Pass | YK NS
As a customer I want to have control of my shopping cart so that I can edit/remove items | Given I'm logged in as a customer, when I log out and log back in as the same customer then the contents of my shopping cart are still there | Fail | JM, 3/27, Test failed because solution was not properly implemented | Pass | YK NS
| Given I'm logged in as a customer, when I click the cart button then my cart is displayed | Fail | JM, 3/27, Test failed because solution was not properly implemented | Pass | YK NS
| Given I remove a product in the cart, when it does exist in the system then it returns 200 OK | Pass |  | Pass | YK NS
| Given I remove a product in the cart, when it does not exist in the system then it returns 404 NOT FOUND | Pass |  |  | can't test
| Given I change a product quantity, when it does exist in the system then it returns 200 OK | Pass |  | Pass | YK NS
| Given I change a product quantity in the cart, when it doesn't exist in the account then it returns 404 NOT FOUND | Pass |  |  | can't test
As an account owner I want to accept offers from other account owners so that I can get cards I want by trading ones I don’t want. | Given I have the product requested in a trade offer when I accept the trade then I expect to swap cards with the other user and resolve the offer
Given I own products when make a trade offer then I can receive cards from the offer I made.
Give I have the product requested in a trade offer when I decline the trade then I expect to keep my card and resolve the offer
As a Customer I want to check out all items in my cart so I review them, add my personal info, and purchase them. | Given I have items in my cart, when I click check out then I am taken to a page where i can enter my name, billing address, and select my desired payment type
Given I am on the checkout page, when I click checkout then my items are purchased and removed from the store inventory
As a user I want to be able to purchase my items so that I can add to my collection. | Given I'm buying some products when I check out then the products I purchased are in my account inventory.